## Days
BALI IN BENGALURU · ARTIST TOUR · DAILY ROUTINE
Travel and event routine, day by day
25 artists + 2 volunteers · staying at Jana Seva Vidya Kendra · from leaving the stay to leaving the last venue, dinner included · one tab per day
Date | Day | Events | Leave the stay | Last venue | Dinner | Note
Wed, 30 Sep | Arrival |  | 4.25pm |  | 7.30pm · Dinner at the stay
Thu, 1 Oct | Rest day |  |  |  |  | Rest day at the stay · no travel
Fri, 2 Oct | Show day | Photoshoot 7.00am | 5.40am | Mandala Cultural Centre | 2.20pm · Dinner near Mandala Cultural Centre | Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
Sat, 3 Oct | Show day | An Evening of Kecak - Inaugural Public Performance 5.30pm | 2.35pm | Orion Mall | 7.50pm · Dinner near Orion Mall | Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
Sun, 4 Oct | Show day | Dance Movement Workshop 9.00am; Shadow Puppetry Performance 3.30pm | 7.30am | Jagriti Theatre | 9.50pm · Dinner near Jagriti Theatre (late return)
Mon, 5 Oct | Rest day |  |  |  |  | Rest day at the stay · no travel
Tue, 6 Oct | Show day | Kecak Workshop 6.00pm | 4.30pm | PCPA (Prestige Centre for Performing Arts) | 9.20pm · Dinner near PCPA (Prestige Centre for Performing Arts) | Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
Wed, 7 Oct | Show day | Kecak Workshop 6.00pm | 4.30pm | PCPA (Prestige Centre for Performing Arts) | 9.20pm · Dinner near PCPA (Prestige Centre for Performing Arts) | Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
Thu, 8 Oct | Show day | Lecture Demonstration 5.00pm | 3.55pm | Indian Music Experience Museum | 6.40pm · Dinner near Indian Music Experience Museum | Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
Fri, 9 Oct | Show day | Workshop for Students 10.00am; Traditional Balinese Dance 5.00pm | 8.30am | Meenakshi Rangamancha | 7.20pm · Dinner near Meenakshi Rangamancha | Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
Sat, 10 Oct | Show day | Dance Movement Workshop - 2 4.00pm | 2.30pm |  | 7.20pm · Dinner before leaving | Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
Sun, 11 Oct | Show day | Shadow Puppetry Workshop 10.00am; Kecak Performance 5.30pm | 8.30am | PCPA (Prestige Centre for Performing Arts) | 7.50pm · Dinner near PCPA (Prestige Centre for Performing Arts) | Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
Mon, 12 Oct | Show day | Shadow Puppetry Workshop 10.00am; Indonesian × Indian Puppetry Act 6.30pm | 8.30am | Mandala Cultural Centre | 8.50pm · Dinner near Mandala Cultural Centre | Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
Tue, 13 Oct | Show day | Traditional Balinese Dance × Yakshagana Performance 6.00pm | 3.05pm | Chowdiah Memorial Hall | 8.20pm · Dinner near Chowdiah Memorial Hall | Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
Wed, 14 Oct | Show day | Mask Making Workshop 10.00am; Gamelan workshop 5.00pm | 8.30am | Jama The Studio | 7.50pm · Dinner near Jama The Studio | Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
Thu, 15 Oct | Show day | Mask Making Workshop 10.00am; Balinese Shadow Puppetry Performance 7.30pm | 8.30am | Yuvapatha | 9.50pm · Dinner near Yuvapatha | No return to the stay tonight: the overnight coach to Manipal University leaves from Yuvapatha at 11.45pm — pack for Manipal in the morning.
Fri, 16 Oct | Out of town | A Day in Manipal | 7.07am | Manipal University | 7.00pm · Dinner near Manipal University | “A Day in Manipal” has no time in the sheet; assumed a day programme from 10.00am. · 6 Yakshagana artists (local) travel with the group today — 31 in the vehicles. · Overnight travel both ways: sleep
Sat, 17 Oct | Show day | Balinese Dance Demonstration 4.00pm | 5.32am | Indian Music Experience Museum | 6.20pm · Dinner near Indian Music Experience Museum | Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
Sun, 18 Oct | Show day | The Finale 6.30pm | 3.35pm |  | 8.50pm · Dinner before leaving | Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
Mon, 19 Oct | Departure |  | 8.14pm |  | 6.49pm · Dinner at the stay

## 30 Sep
BALI IN BENGALURU · DAILY ROUTINE
Wed, 30 Sep
Arrival day
From | To | What | Where / detail
3.10pm | 4.25pm | LAND AT KEMPEGOWDA INTERNATIONAL AIRPORT
4.25pm | 5.28pm | → Leave Kempegowda International Airport for the stay | 1 h 03 · 48 km · live traffic · 10 min loading first
5.28pm | 6.58pm | Check in at the stay, settle in | Rooms, luggage, a first briefing.
7.30pm | 8.30pm | Dinner at the stay

## 01 Oct
BALI IN BENGALURU · DAILY ROUTINE
Thu, 1 Oct
Rest day at the stay
• Rest day at the stay · no travel
From | To | What | Where / detail
Rest day at the stay · no travel

## 02 Oct
BALI IN BENGALURU · DAILY ROUTINE
Fri, 2 Oct
Photoshoot 7.00am
• 6 Yakshagana artists (local) perform with the group today and travel on their own.
• Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
From | To | What | Where / detail
5.40am | 6.24am | → Leave the stay for Mandala Cultural Centre | 34 min · 25 km · live traffic · 10 min loading first
6.24am | 6.34am | Instrument & stage set-up
6.34am | 6.49am | Costume, make-up, warm-up & call
6.49am | 7.00am | Spare time at the venue
7.00am | 2.00pm | PHOTOSHOOT | Internal · Mandala Cultural Centre, Talaghattapura, Kanakapura Road
12.00pm | 1.00pm | Lunch at the venue (packed) | During “Photoshoot” — arrange packed lunch.
2.00pm | 2.10pm | Costume off, make-up removal & change
2.10pm | 2.20pm | Wrap — pack, meet people, load-out
2.20pm | 3.20pm | Dinner near Mandala Cultural Centre | added: the plan has dinner back at the stay

## 03 Oct
BALI IN BENGALURU · DAILY ROUTINE
Sat, 3 Oct
An Evening of Kecak - Inaugural Public Performance 5.30pm
• Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
From | To | What | Where / detail
2.35pm | 3.11pm | → Leave the stay for Orion Mall | 26 min · 18 km · live traffic · 10 min loading first
3.11pm | 3.41pm | Instrument & stage set-up
3.41pm | 4.11pm | Sound check
4.11pm | 5.11pm | Costume, make-up, warm-up & call
5.11pm | 5.30pm | Spare time at the venue
5.30pm | 7.00pm | AN EVENING OF KECAK - INAUGURAL PUBLIC PERFORMANCE | Performance · Orion Mall, Rajajinagar · 25 artists
7.00pm | 7.20pm | Costume off, make-up removal & change
7.20pm | 7.50pm | Wrap — pack, meet people, load-out
7.50pm | 8.50pm | Dinner near Orion Mall | added: the plan has dinner back at the stay

## 04 Oct
BALI IN BENGALURU · DAILY ROUTINE
Sun, 4 Oct
Dance Movement Workshop 9.00am · Shadow Puppetry Performance 3.30pm
From | To | What | Where / detail
7.30am | 8.18am | → Leave the stay for Drishti Art Centre | 38 min · 24 km · live traffic · 10 min loading first
8.18am | 8.28am | Instrument & stage set-up
8.28am | 8.38am | Sound check
8.38am | 8.53am | Costume, make-up, warm-up & call
8.53am | 9.00am | Spare time at the venue
9.00am | 12.30pm | DANCE MOVEMENT WORKSHOP | Workshop · Drishti Art Centre, Sahakara Nagar · 25 artists
12.00pm | 1.00pm | Lunch at the venue (packed) | During “Dance Movement Workshop” — arrange packed lunch.
12.30pm | 12.35pm | Costume off, make-up removal & change
12.35pm | 12.50pm | Wrap — pack, meet people, load-out
12.50pm | 1.31pm | → Leave Drishti Art Centre for Jagriti Theatre | 41 min · 29 km · live traffic
1.31pm | 2.01pm | Instrument & stage set-up
2.01pm | 2.31pm | Sound check
2.31pm | 3.30pm | Costume, make-up, warm-up & call
3.30pm | 5.00pm | SHADOW PUPPETRY PERFORMANCE — SHOW 1 | Performance · Jagriti Theatre, Whitefield
7.30pm | 9.00pm | SHADOW PUPPETRY PERFORMANCE — SHOW 2 | Performance · Jagriti Theatre, Whitefield
9.00pm | 9.20pm | Costume off, make-up removal & change
9.20pm | 9.50pm | Wrap — pack, meet people, load-out
9.50pm | 10.50pm | Dinner near Jagriti Theatre (late return)

## 05 Oct
BALI IN BENGALURU · DAILY ROUTINE
Mon, 5 Oct
Rest day at the stay
• Rest day at the stay · no travel
From | To | What | Where / detail
Rest day at the stay · no travel

## 06 Oct
BALI IN BENGALURU · DAILY ROUTINE
Tue, 6 Oct
Kecak Workshop 6.00pm
• Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
From | To | What | Where / detail
4.30pm | 5.19pm | → Leave the stay for PCPA (Prestige Centre for Performing Arts) | 39 min · 26 km · live traffic · 10 min loading first
5.19pm | 5.29pm | Instrument & stage set-up
5.29pm | 5.39pm | Sound check
5.39pm | 5.54pm | Costume, make-up, warm-up & call
5.54pm | 6.00pm | Spare time at the venue
6.00pm | 9.00pm | KECAK WORKSHOP | Workshop · PCPA (Prestige Centre for Performing Arts), Konanakunte, Kanakapura Road · 25 artists
9.00pm | 9.05pm | Costume off, make-up removal & change
9.05pm | 9.20pm | Wrap — pack, meet people, load-out
9.20pm | 10.20pm | Dinner near PCPA (Prestige Centre for Performing Arts) | added: the plan has dinner back at the stay

## 07 Oct
BALI IN BENGALURU · DAILY ROUTINE
Wed, 7 Oct
Kecak Workshop 6.00pm
• Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
From | To | What | Where / detail
4.30pm | 5.19pm | → Leave the stay for PCPA (Prestige Centre for Performing Arts) | 39 min · 26 km · live traffic · 10 min loading first
5.19pm | 5.29pm | Instrument & stage set-up
5.29pm | 5.39pm | Sound check
5.39pm | 5.54pm | Costume, make-up, warm-up & call
5.54pm | 6.00pm | Spare time at the venue
6.00pm | 9.00pm | KECAK WORKSHOP | Workshop · PCPA (Prestige Centre for Performing Arts), Konanakunte, Kanakapura Road · 25 artists
9.00pm | 9.05pm | Costume off, make-up removal & change
9.05pm | 9.20pm | Wrap — pack, meet people, load-out
9.20pm | 10.20pm | Dinner near PCPA (Prestige Centre for Performing Arts) | added: the plan has dinner back at the stay

## 08 Oct
BALI IN BENGALURU · DAILY ROUTINE
Thu, 8 Oct
Lecture Demonstration 5.00pm
• Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
From | To | What | Where / detail
3.55pm | 4.46pm | → Leave the stay for Indian Music Experience Museum | 41 min · 27 km · live traffic · 10 min loading first
4.46pm | 4.56pm | Sound check
4.56pm | 5.00pm | Spare time at the venue
5.00pm | 6.30pm | LECTURE DEMONSTRATION | Talk · Indian Music Experience Museum, JP Nagar 7th Phase · 2 artists
6.30pm | 6.40pm | Wrap — pack, meet people, load-out
6.40pm | 7.40pm | Dinner near Indian Music Experience Museum | added: the plan has dinner back at the stay

## 09 Oct
BALI IN BENGALURU · DAILY ROUTINE
Fri, 9 Oct
Workshop for Students 10.00am · Traditional Balinese Dance 5.00pm
• Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
From | To | What | Where / detail
8.30am | 9.12am | → Leave the stay for Kumarans School | 32 min · 22 km · live traffic · 10 min loading first
9.12am | 9.22am | Instrument & stage set-up
9.22am | 9.32am | Sound check
9.32am | 9.47am | Costume, make-up, warm-up & call
9.47am | 10.00am | Spare time at the venue
10.00am | 1.00pm | WORKSHOP FOR STUDENTS | Workshop · Kumarans School, Chikkalasandra · 25 artists
1.00pm | 1.05pm | Costume off, make-up removal & change
1.05pm | 1.20pm | Wrap — pack, meet people, load-out
1.20pm | 2.50pm | Hold in town near Kumarans School
1.20pm | 2.20pm | Lunch near Kumarans School
2.50pm | 3.00pm | → Leave Kumarans School for Meenakshi Rangamancha | 10 min · 5 km · live traffic
3.00pm | 3.30pm | Instrument & stage set-up
3.30pm | 4.00pm | Sound check
4.00pm | 5.00pm | Costume, make-up, warm-up & call
5.00pm | 6.30pm | TRADITIONAL BALINESE DANCE | Performance · Meenakshi Rangamancha, Doddakallasandra, Kanakapura Road · 25 artists
6.30pm | 6.50pm | Costume off, make-up removal & change
6.50pm | 7.20pm | Wrap — pack, meet people, load-out
7.20pm | 8.20pm | Dinner near Meenakshi Rangamancha | added: the plan has dinner back at the stay

## 10 Oct
BALI IN BENGALURU · DAILY ROUTINE
Sat, 10 Oct
Dance Movement Workshop - 2 4.00pm
• Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
From | To | What | Where / detail
2.30pm | 3.25pm | → Leave the stay for MLA College, Malleswaram | travel time unknown
3.25pm | 3.35pm | Instrument & stage set-up
3.35pm | 3.45pm | Sound check
3.45pm | 4.00pm | Costume, make-up, warm-up & call
4.00pm | 7.00pm | DANCE MOVEMENT WORKSHOP - 2 | Workshop
7.00pm | 7.05pm | Costume off, make-up removal & change
7.05pm | 7.20pm | Wrap — pack, meet people, load-out
7.20pm | 8.20pm | Dinner before leaving | added: the plan has dinner back at the stay

## 11 Oct
BALI IN BENGALURU · DAILY ROUTINE
Sun, 11 Oct
Shadow Puppetry Workshop 10.00am · Kecak Performance 5.30pm
• Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
From | To | What | Where / detail
8.30am | 9.14am | → Leave the stay for Mandala Cultural Centre | 34 min · 25 km · live traffic · 10 min loading first
9.14am | 9.24am | Instrument & stage set-up
9.24am | 9.34am | Sound check
9.34am | 9.49am | Costume, make-up, warm-up & call
9.49am | 10.00am | Spare time at the venue
10.00am | 1.00pm | SHADOW PUPPETRY WORKSHOP | Workshop · Mandala Cultural Centre, Talaghattapura, Kanakapura Road
1.00pm | 1.05pm | Costume off, make-up removal & change
1.05pm | 1.20pm | Wrap — pack, meet people, load-out
1.20pm | 3.06pm | Hold in town near Mandala Cultural Centre
1.20pm | 2.20pm | Lunch near Mandala Cultural Centre
3.06pm | 3.15pm | → Leave Mandala Cultural Centre for PCPA (Prestige Centre for Performing Arts) | 9 min · 5 km · live traffic
3.15pm | 4.00pm | Instrument & stage set-up
4.00pm | 4.30pm | Sound check
4.30pm | 5.30pm | Costume, make-up, warm-up & call
5.30pm | 7.00pm | KECAK PERFORMANCE | Performance · PCPA (Prestige Centre for Performing Arts), Konanakunte, Kanakapura Road · 12 artists · Kecak troupe A
7.00pm | 7.20pm | Costume off, make-up removal & change
7.20pm | 7.50pm | Wrap — pack, meet people, load-out
7.50pm | 8.50pm | Dinner near PCPA (Prestige Centre for Performing Arts) | added: the plan has dinner back at the stay

## 12 Oct
BALI IN BENGALURU · DAILY ROUTINE
Mon, 12 Oct
Shadow Puppetry Workshop 10.00am · Indonesian × Indian Puppetry Act 6.30pm
• Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
From | To | What | Where / detail
8.30am | 9.14am | → Leave the stay for Mandala Cultural Centre | 34 min · 25 km · live traffic · 10 min loading first
9.14am | 9.24am | Instrument & stage set-up
9.24am | 9.34am | Sound check
9.34am | 9.49am | Costume, make-up, warm-up & call
9.49am | 10.00am | Spare time at the venue
10.00am | 1.00pm | SHADOW PUPPETRY WORKSHOP | Workshop · Mandala Cultural Centre, Talaghattapura, Kanakapura Road
1.00pm | 1.05pm | Costume off, make-up removal & change
1.05pm | 1.20pm | Wrap — pack, meet people, load-out
1.20pm | 4.30pm | Hold at Mandala Cultural Centre
1.20pm | 2.20pm | Lunch near Mandala Cultural Centre
4.30pm | 4.30pm | → Leave Mandala Cultural Centre for Mandala Cultural Centre | 0 min · 0 km
4.30pm | 5.00pm | Instrument & stage set-up
5.00pm | 5.30pm | Sound check
5.30pm | 6.30pm | Costume, make-up, warm-up & call
6.30pm | 8.00pm | INDONESIAN × INDIAN PUPPETRY ACT | Performance · Mandala Cultural Centre, Talaghattapura, Kanakapura Road
8.00pm | 8.20pm | Costume off, make-up removal & change
8.20pm | 8.50pm | Wrap — pack, meet people, load-out
8.50pm | 9.50pm | Dinner near Mandala Cultural Centre | added: the plan has dinner back at the stay

## 13 Oct
BALI IN BENGALURU · DAILY ROUTINE
Tue, 13 Oct
Traditional Balinese Dance × Yakshagana Performance 6.00pm
• 6 Yakshagana artists (local) perform with the group today and travel on their own.
• Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
From | To | What | Where / detail
3.05pm | 3.48pm | → Leave the stay for Chowdiah Memorial Hall | 33 min · 21 km · live traffic · 10 min loading first
3.48pm | 4.18pm | Instrument & stage set-up
4.18pm | 4.48pm | Sound check
4.48pm | 5.48pm | Costume, make-up, warm-up & call
5.48pm | 6.00pm | Spare time at the venue
6.00pm | 7.30pm | TRADITIONAL BALINESE DANCE × YAKSHAGANA PERFORMANCE | Performance · Chowdiah Memorial Hall, Vyalikaval, Malleshwaram · 25 artists
7.30pm | 7.50pm | Costume off, make-up removal & change
7.50pm | 8.20pm | Wrap — pack, meet people, load-out
8.20pm | 9.20pm | Dinner near Chowdiah Memorial Hall | added: the plan has dinner back at the stay

## 14 Oct
BALI IN BENGALURU · DAILY ROUTINE
Wed, 14 Oct
Mask Making Workshop 10.00am · Gamelan workshop 5.00pm
• Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
From | To | What | Where / detail
8.30am | 9.16am | → Leave the stay for PARSEC, Jayanagar (Maker's Adda) | 36 min · 25 km · live traffic · 10 min loading first
9.16am | 9.26am | Instrument & stage set-up
9.26am | 9.36am | Sound check
9.36am | 9.51am | Costume, make-up, warm-up & call
9.51am | 10.00am | Spare time at the venue
10.00am | 1.00pm | MASK MAKING WORKSHOP | Workshop · PARSEC, Jayanagar (Maker's Adda), Jayanagar 7th Block · 25 artists
1.00pm | 1.05pm | Costume off, make-up removal & change
1.05pm | 1.20pm | Wrap — pack, meet people, load-out
1.20pm | 4.21pm | Hold in town near PARSEC, Jayanagar (Maker's Adda)
1.20pm | 2.20pm | Lunch near PARSEC, Jayanagar (Maker's Adda)
4.21pm | 4.25pm | → Leave PARSEC, Jayanagar (Maker's Adda) for Jama The Studio | 4 min · 2 km · live traffic
4.25pm | 4.35pm | Instrument & stage set-up
4.35pm | 4.45pm | Sound check
4.45pm | 5.00pm | Costume, make-up, warm-up & call
5.00pm | 7.30pm | GAMELAN WORKSHOP | Workshop · Jama The Studio, Jayanagar 2nd Block · 25 artists
7.30pm | 7.35pm | Costume off, make-up removal & change
7.35pm | 7.50pm | Wrap — pack, meet people, load-out
7.50pm | 8.50pm | Dinner near Jama The Studio | added: the plan has dinner back at the stay

## 15 Oct
BALI IN BENGALURU · DAILY ROUTINE
Thu, 15 Oct
Mask Making Workshop 10.00am · Balinese Shadow Puppetry Performance 7.30pm
From | To | What | Where / detail
8.30am | 9.16am | → Leave the stay for PARSEC, Jayanagar (Maker's Adda) | 36 min · 25 km · live traffic · 10 min loading first
9.16am | 9.26am | Instrument & stage set-up
9.26am | 9.36am | Sound check
9.36am | 9.51am | Costume, make-up, warm-up & call
9.51am | 10.00am | Spare time at the venue
10.00am | 1.00pm | MASK MAKING WORKSHOP | Workshop · PARSEC, Jayanagar (Maker's Adda), Jayanagar 7th Block · 25 artists
1.00pm | 1.05pm | Costume off, make-up removal & change
1.05pm | 1.20pm | Wrap — pack, meet people, load-out
1.20pm | 1.54pm | → Back to the stay | 34 min · 24 km · live traffic
1.54pm | 4.41pm | At the stay — rest
1.54pm | 2.54pm | Lunch at the stay
4.32pm | 5.21pm | → Leave the stay for Yuvapatha | 39 min · 26 km · live traffic · 10 min loading first
5.21pm | 5.51pm | Instrument & stage set-up
5.51pm | 6.21pm | Sound check
6.21pm | 7.21pm | Costume, make-up, warm-up & call
7.21pm | 7.30pm | Spare time at the venue
7.30pm | 9.00pm | BALINESE SHADOW PUPPETRY PERFORMANCE | Performance · Yuvapatha, Jayanagar · 25 artists
9.00pm | 9.20pm | Costume off, make-up removal & change
9.20pm | 9.50pm | Wrap — pack, meet people, load-out
9.50pm | 10.50pm | Dinner near Yuvapatha
10.50pm | 11.45pm | Wait for the coach at Yuvapatha
11.45pm |  | → Leave Yuvapatha for Manipal University — overnight drive | 7 h 22 · 414 km · live traffic · sleep on the road

## 16 Oct
BALI IN BENGALURU · DAILY ROUTINE
Fri, 16 Oct
A Day in Manipal
• 6 Yakshagana artists (local) travel with the group today — 31 in the vehicles.
From | To | What | Where / detail
7.07am |  | → Arrive Manipal University after the overnight drive | 7 h 22 · 414 km · live traffic · left Yuvapatha 11.45pm on Thu, 15 Oct
7.07am | 8.37am | Freshen up & breakfast on arrival
8.37am | 9.07am | Instrument & stage set-up
9.07am | 9.37am | Sound check
9.37am | 10.00am | Costume, make-up, warm-up & call
10.00am | 4.00pm | A DAY IN MANIPAL | Performance · Manipal University, Manipal, Udupi (out of town) · 25 artists
12.00pm | 1.00pm | Lunch at the venue (packed) | During “A Day in Manipal” — arrange packed lunch.
4.00pm | 4.20pm | Costume off, make-up removal & change
4.20pm | 4.50pm | Wrap — pack, meet people, load-out
7.00pm | 8.00pm | Dinner near Manipal University
8.00pm | 11.45pm | Rest before the night drive
11.45pm |  | → Leave for the stay — overnight drive | 6 h 52 · 387 km · live traffic · home about 5.32am (+1)

## 17 Oct
BALI IN BENGALURU · DAILY ROUTINE
Sat, 17 Oct
Balinese Dance Demonstration 4.00pm
• Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
From | To | What | Where / detail
5.32am |  | → Arrive back at the stay from Manipal University | overnight drive · rest before the day starts
7.30am | 8.10am | Breakfast at the stay
8.10am | 12.35pm | Free at the stay — rehearsal, rest
12.00pm | 1.00pm | Lunch at the stay
12.35pm | 1.05pm | Get ready · costumes & personal kit to the vehicle
1.05pm | 1.56pm | → Leave the stay for Indian Music Experience Museum | 41 min · 27 km · live traffic · 10 min loading first
1.56pm | 2.26pm | Instrument & stage set-up
2.26pm | 2.56pm | Sound check
2.56pm | 3.56pm | Costume, make-up, warm-up & call
3.56pm | 4.00pm | Spare time at the venue
4.00pm | 5.30pm | BALINESE DANCE DEMONSTRATION | Performance · Indian Music Experience Museum, JP Nagar 7th Phase · 25 artists
5.30pm | 5.50pm | Costume off, make-up removal & change
5.50pm | 6.20pm | Wrap — pack, meet people, load-out
6.20pm | 7.20pm | Dinner near Indian Music Experience Museum | added: the plan has dinner back at the stay

## 18 Oct
BALI IN BENGALURU · DAILY ROUTINE
Sun, 18 Oct
The Finale 6.30pm
• Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
From | To | What | Where / detail
3.35pm | 4.30pm | → Leave the stay for Suchitra Cinema and Cultural Academy - Amphitheatre | travel time unknown
4.30pm | 5.00pm | Instrument & stage set-up
5.00pm | 5.30pm | Sound check
5.30pm | 6.30pm | Costume, make-up, warm-up & call
6.30pm | 8.00pm | THE FINALE | Performance
8.00pm | 8.20pm | Costume off, make-up removal & change
8.20pm | 8.50pm | Wrap — pack, meet people, load-out
8.50pm | 9.50pm | Dinner before leaving | added: the plan has dinner back at the stay

## 19 Oct
BALI IN BENGALURU · DAILY ROUTINE
Mon, 19 Oct
Departure day
From | To | What | Where / detail
6.49pm | 7.49pm | Dinner at the stay
8.04pm | 8.14pm | Load luggage into the vehicles
8.14pm | 9.13pm | → Leave the stay for Kempegowda International Airport | 59 min · 48 km · live traffic
9.13pm | 12.50am (+1) | Check-in, immigration, security | 180 min before the flight.
12.50am (+1) |  | FLIGHT DEPARTS 12.50AM (+1)