## Days
BALI IN BENGALURU · ARTIST TOUR · DAILY ROUTINE
Travel and event routine, day by day
25 artists + 2 volunteers · staying at Jana Seva Vidya Kendra · from leaving the stay to leaving the last venue, dinner included · one tab per day
Date | Day | Events | Leave the stay | Last venue | Dinner | Note
Wed, 30 Sep | Arrival |  | 4.25pm |  | 7.30pm · Dinner at the stay
Thu, 1 Oct | Rest day |  |  |  |  | Rest day at the stay · no travel
Fri, 2 Oct | Show day | Photoshoot 7.00am | 5.40am | Mandala Cultural Centre | 2.20pm · Dinner near Mandala Cultural Centre | Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
Sat, 3 Oct | Show day | An Evening of Kecak - Inaugural Public Performance 6.00pm | 2.58pm | Orion Mall | 8.20pm · Dinner near Orion Mall | Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
Sun, 4 Oct | Show day | Dance Movement Workshop 9.00am; Indonesian Shadow Puppetry Performance 3.30pm | 7.30am | Jagriti Theatre | 9.50pm · Dinner near Jagriti Theatre (late return) | “Indonesian Shadow Puppetry Performance”: arrives 1.51pm, 21 min late for the 120 min preparation. · Late night: lights out at 1.16am (+1).
Mon, 5 Oct | Rest day |  |  |  |  | Rest day at the stay · no travel
Tue, 6 Oct | Show day | Kecak Workshop 6.00pm | 4.23pm | PCPA (Prestige Centre for Performing Arts) | 10.20pm · Dinner near PCPA (Prestige Centre for Performing Arts) (late return) | Late night: lights out at 1.06am (+1).
Wed, 7 Oct | Show day | Kecak Workshop 6.00pm | 4.21pm | PCPA (Prestige Centre for Performing Arts) | 10.20pm · Dinner near PCPA (Prestige Centre for Performing Arts) (late return) | Short night: 5 h 54 between lights out (1.06am (+1)) and wake-up. · Late night: lights out at 1.06am (+1).
Thu, 8 Oct | Show day | Lecture Demonstration 6.00pm | 4.05pm | Indian Music Experience Museum | 7.50pm · Dinner near Indian Music Experience Museum | Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
Fri, 9 Oct | Show day | Workshop for Students 10.00am; Traditional Balinese Dance 7.00pm | 8.30am | Meenakshi Rangamancha | 9.20pm · Dinner near Meenakshi Rangamancha | Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
Sat, 10 Oct | Rest day |  |  |  |  | Rest day at the stay · no travel
Sun, 11 Oct | Show day | Balinese Shadow Puppetry Workshop 10.00am; Kecak Performance 7.00pm | 8.30am | PCPA (Prestige Centre for Performing Arts) | 9.20pm · Dinner near PCPA (Prestige Centre for Performing Arts) | Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
Mon, 12 Oct | Show day | Balinese Shadow Puppetry Workshop 10.00am; Indonesian × Indian Shadow Puppetry Performance 7.30pm | 8.30am | Mandala Cultural Centre | 9.50pm · Dinner near Mandala Cultural Centre (late return)
Tue, 13 Oct | Show day | Traditional Balinese Dance × Yakshagana Performance 7.00pm | 3.58pm | Chowdiah Memorial Hall | 9.50pm · Dinner near Chowdiah Memorial Hall (late return) | 6 Yakshagana artists (local) perform with the group today and travel on their own.
Wed, 14 Oct | Show day | Mask Making Workshop 10.00am; Gamelan workshop 6.00pm | 8.15am | Jama The Studio | 8.20pm · Dinner near Jama The Studio | Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
Thu, 15 Oct | Show day | Mask Making Workshop 10.00am; Balinese Shadow Puppetry Performance 7.30pm | 8.15am | Yuvapatha | 9.50pm · Dinner near Yuvapatha | No return to the stay tonight: the overnight coach to Manipal University leaves from Yuvapatha at 11.45pm — pack for Manipal in the morning.
Fri, 16 Oct | Out of town | A Day in Manipal | 7.17am | Manipal University | 7.00pm · Dinner near Manipal University | “A Day in Manipal” has no time in the sheet; assumed a day programme from 10.00am. · 6 Yakshagana artists (local) travel with the group today — 31 in the vehicles. · Overnight travel both ways: sleep
Sat, 17 Oct | Show day | Balinese Dance Demonstration 4.00pm | 5.32am | Indian Music Experience Museum | 6.20pm · Dinner near Indian Music Experience Museum | Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
Sun, 18 Oct | Show day | Closing Day 11.00am | 9.08am | Sabha Bengaluru | 10.20pm · Dinner near Sabha Bengaluru (late return) | Late night: lights out at 1.16am (+1).
Mon, 19 Oct | Departure |  | 8.14pm |  | 6.49pm · Dinner at the stay

## 30 Sep
BALI IN BENGALURU · DAILY ROUTINE
Wed, 30 Sep
Arrival day
From | To | What | Where / detail
3.10pm | 4.25pm | LAND AT KEMPEGOWDA INTERNATIONAL AIRPORT
4.25pm | 6.00pm | → Leave Kempegowda International Airport for the stay | 1 h 35 · 52 km · typical traffic for the day · 10 min loading first
6.00pm | 7.30pm | Check in at the stay, settle in | Rooms, luggage, a first briefing.
7.30pm | 8.30pm | Dinner at the stay

## 01 Oct
BALI IN BENGALURU · DAILY ROUTINE
Thu, 1 Oct
Rest day at the stay
• Rest day at the stay · no travel
From | To | What | Where / detail
Rest day at the stay · no travel

## 02 Oct
BALI IN BENGALURU · DAILY ROUTINE
Fri, 2 Oct
Photoshoot 7.00am
• 6 Yakshagana artists (local) perform with the group today and travel on their own.
• Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
From | To | What | Where / detail
5.40am | 6.21am | → Leave the stay for Mandala Cultural Centre | 31 min · 25 km · typical traffic for the day · 10 min loading first
6.21am | 6.31am | Instrument & stage set-up
6.31am | 6.46am | Costume, make-up, warm-up & call
6.46am | 7.00am | Spare time at the venue
7.00am | 2.00pm | PHOTOSHOOT | Internal · Mandala Cultural Centre, Talaghattapura, Kanakapura Road
12.00pm | 1.00pm | Lunch at the venue (packed) | During “Photoshoot” — arrange packed lunch.
2.00pm | 2.10pm | Costume off, make-up removal & change
2.10pm | 2.20pm | Wrap — pack, meet people, load-out
2.20pm | 3.20pm | Dinner near Mandala Cultural Centre | added: the plan has dinner back at the stay

## 03 Oct
BALI IN BENGALURU · DAILY ROUTINE
Sat, 3 Oct
An Evening of Kecak - Inaugural Public Performance 6.00pm
• Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
From | To | What | Where / detail
2.58pm | 4.00pm | → Leave the stay for Orion Mall | 52 min · 24 km · typical traffic for the day · 10 min loading first
4.00pm | 4.30pm | Instrument & stage set-up
4.30pm | 5.00pm | Sound check
5.00pm | 6.00pm | Costume, make-up, warm-up & call
6.00pm | 7.30pm | AN EVENING OF KECAK - INAUGURAL PUBLIC PERFORMANCE | Performance · Orion Mall, Rajajinagar · 25 artists
7.30pm | 7.50pm | Costume off, make-up removal & change
7.50pm | 8.20pm | Wrap — pack, meet people, load-out
8.20pm | 9.20pm | Dinner near Orion Mall | added: the plan has dinner back at the stay

## 04 Oct
BALI IN BENGALURU · DAILY ROUTINE
Sun, 4 Oct
Dance Movement Workshop 9.00am · Indonesian Shadow Puppetry Performance 3.30pm
From | To | What | Where / detail
7.30am | 8.24am | → Leave the stay for Drishti Art Centre | 44 min · 28 km · typical traffic for the day · 10 min loading first
8.24am | 8.34am | Instrument & stage set-up
8.34am | 8.44am | Sound check
8.44am | 8.59am | Costume, make-up, warm-up & call
9.00am | 12.30pm | DANCE MOVEMENT WORKSHOP | Workshop · Drishti Art Centre, Sahakara Nagar · 25 artists
12.00pm | 1.00pm | Lunch at the venue (packed) | During “Dance Movement Workshop” — arrange packed lunch.
12.30pm | 12.35pm | Costume off, make-up removal & change
12.35pm | 12.50pm | Wrap — pack, meet people, load-out
12.50pm | 1.51pm | → Leave Drishti Art Centre for Jagriti Theatre | 1 h 01 · 26 km · typical traffic for the day
1.51pm | 2.21pm | Instrument & stage set-up
2.21pm | 2.51pm | Sound check
2.51pm | 3.30pm | Costume, make-up, warm-up & call
3.30pm | 5.00pm | INDONESIAN SHADOW PUPPETRY PERFORMANCE — SHOW 1 | Performance · Jagriti Theatre, Whitefield · 25 artists
7.30pm | 9.00pm | INDONESIAN SHADOW PUPPETRY PERFORMANCE — SHOW 2 | Performance · Jagriti Theatre, Whitefield · 25 artists
9.00pm | 9.20pm | Costume off, make-up removal & change
9.20pm | 9.50pm | Wrap — pack, meet people, load-out
9.50pm | 10.50pm | Dinner near Jagriti Theatre (late return)

## 05 Oct
BALI IN BENGALURU · DAILY ROUTINE
Mon, 5 Oct
Rest day at the stay
• Rest day at the stay · no travel
From | To | What | Where / detail
Rest day at the stay · no travel

## 06 Oct
BALI IN BENGALURU · DAILY ROUTINE
Tue, 6 Oct
Kecak Workshop 6.00pm
From | To | What | Where / detail
4.23pm | 5.25pm | → Leave the stay for PCPA (Prestige Centre for Performing Arts) | 52 min · 30 km · typical traffic for the day · 10 min loading first
5.25pm | 5.35pm | Instrument & stage set-up
5.35pm | 5.45pm | Sound check
5.45pm | 6.00pm | Costume, make-up, warm-up & call
6.00pm | 10.00pm | KECAK WORKSHOP | Workshop · PCPA (Prestige Centre for Performing Arts), Konanakunte, Kanakapura Road · 25 artists
10.00pm | 10.05pm | Costume off, make-up removal & change
10.05pm | 10.20pm | Wrap — pack, meet people, load-out
10.20pm | 11.20pm | Dinner near PCPA (Prestige Centre for Performing Arts) (late return)

## 07 Oct
BALI IN BENGALURU · DAILY ROUTINE
Wed, 7 Oct
Kecak Workshop 6.00pm
From | To | What | Where / detail
4.21pm | 5.25pm | → Leave the stay for PCPA (Prestige Centre for Performing Arts) | 54 min · 30 km · typical traffic for the day · 10 min loading first
5.25pm | 5.35pm | Instrument & stage set-up
5.35pm | 5.45pm | Sound check
5.45pm | 6.00pm | Costume, make-up, warm-up & call
6.00pm | 10.00pm | KECAK WORKSHOP | Workshop · PCPA (Prestige Centre for Performing Arts), Konanakunte, Kanakapura Road · 25 artists
10.00pm | 10.05pm | Costume off, make-up removal & change
10.05pm | 10.20pm | Wrap — pack, meet people, load-out
10.20pm | 11.20pm | Dinner near PCPA (Prestige Centre for Performing Arts) (late return)

## 08 Oct
BALI IN BENGALURU · DAILY ROUTINE
Thu, 8 Oct
Lecture Demonstration 6.00pm
• Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
From | To | What | Where / detail
4.05pm | 5.20pm | → Leave the stay for Indian Music Experience Museum | 1 h 05 · 37 km · typical traffic for the day · 10 min loading first
5.20pm | 5.30pm | Instrument & stage set-up
5.30pm | 5.40pm | Sound check
5.40pm | 6.00pm | Costume, make-up, warm-up & call
6.00pm | 7.30pm | LECTURE DEMONSTRATION | Talk · Indian Music Experience Museum, JP Nagar 7th Phase · 25 artists
7.30pm | 7.35pm | Costume off, make-up removal & change
7.35pm | 7.50pm | Wrap — pack, meet people, load-out
7.50pm | 8.50pm | Dinner near Indian Music Experience Museum | added: the plan has dinner back at the stay

## 09 Oct
BALI IN BENGALURU · DAILY ROUTINE
Fri, 9 Oct
Workshop for Students 10.00am · Traditional Balinese Dance 7.00pm
• Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
From | To | What | Where / detail
8.30am | 9.25am | → Leave the stay for Kumarans School | 45 min · 28 km · typical traffic for the day · 10 min loading first
9.25am | 9.35am | Instrument & stage set-up
9.35am | 9.45am | Sound check
9.45am | 10.00am | Costume, make-up, warm-up & call
10.00am | 1.00pm | WORKSHOP FOR STUDENTS | Workshop · Kumarans School, Chikkalasandra · 25 artists
1.00pm | 1.05pm | Costume off, make-up removal & change
1.05pm | 1.20pm | Wrap — pack, meet people, load-out
1.20pm | 4.45pm | Hold in town near Kumarans School
1.20pm | 2.20pm | Lunch near Kumarans School
4.45pm | 5.00pm | → Leave Kumarans School for Meenakshi Rangamancha | 15 min · 5 km · typical traffic for the day
5.00pm | 5.30pm | Instrument & stage set-up
5.30pm | 6.00pm | Sound check
6.00pm | 7.00pm | Costume, make-up, warm-up & call
7.00pm | 8.30pm | TRADITIONAL BALINESE DANCE | Performance · Meenakshi Rangamancha, Doddakallasandra, Kanakapura Road · 25 artists
8.30pm | 8.50pm | Costume off, make-up removal & change
8.50pm | 9.20pm | Wrap — pack, meet people, load-out
9.20pm | 10.20pm | Dinner near Meenakshi Rangamancha | added: the plan has dinner back at the stay

## 10 Oct
BALI IN BENGALURU · DAILY ROUTINE
Sat, 10 Oct
Rest day at the stay
• Rest day at the stay · no travel
From | To | What | Where / detail
Rest day at the stay · no travel

## 11 Oct
BALI IN BENGALURU · DAILY ROUTINE
Sun, 11 Oct
Balinese Shadow Puppetry Workshop 10.00am · Kecak Performance 7.00pm
• Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
From | To | What | Where / detail
8.30am | 9.11am | → Leave the stay for Mandala Cultural Centre | 31 min · 25 km · typical traffic for the day · 10 min loading first
9.11am | 9.21am | Instrument & stage set-up
9.21am | 9.31am | Sound check
9.31am | 9.46am | Costume, make-up, warm-up & call
9.46am | 10.00am | Spare time at the venue
10.00am | 1.00pm | BALINESE SHADOW PUPPETRY WORKSHOP | Workshop · Mandala Cultural Centre, Talaghattapura, Kanakapura Road · 25 artists
1.00pm | 1.05pm | Costume off, make-up removal & change
1.05pm | 1.20pm | Wrap — pack, meet people, load-out
1.20pm | 4.28pm | Hold in town near Mandala Cultural Centre
1.20pm | 2.20pm | Lunch near Mandala Cultural Centre
4.28pm | 4.46pm | → Leave Mandala Cultural Centre for PCPA (Prestige Centre for Performing Arts) | 18 min · 5 km · typical traffic for the day
4.46pm | 5.31pm | Instrument & stage set-up
5.31pm | 6.01pm | Sound check
6.01pm | 7.00pm | Costume, make-up, warm-up & call
7.00pm | 8.30pm | KECAK PERFORMANCE | Performance · PCPA (Prestige Centre for Performing Arts), Konanakunte, Kanakapura Road · 12 artists · Kecak troupe A
8.30pm | 8.50pm | Costume off, make-up removal & change
8.50pm | 9.20pm | Wrap — pack, meet people, load-out
9.20pm | 10.20pm | Dinner near PCPA (Prestige Centre for Performing Arts) | added: the plan has dinner back at the stay

## 12 Oct
BALI IN BENGALURU · DAILY ROUTINE
Mon, 12 Oct
Balinese Shadow Puppetry Workshop 10.00am · Indonesian × Indian Shadow Puppetry Performance 7.30pm
From | To | What | Where / detail
8.30am | 9.14am | → Leave the stay for Mandala Cultural Centre | 34 min · 25 km · typical traffic for the day · 10 min loading first
9.14am | 9.24am | Instrument & stage set-up
9.24am | 9.34am | Sound check
9.34am | 9.49am | Costume, make-up, warm-up & call
9.49am | 10.00am | Spare time at the venue
10.00am | 1.00pm | BALINESE SHADOW PUPPETRY WORKSHOP | Workshop · Mandala Cultural Centre, Talaghattapura, Kanakapura Road · 25 artists
1.00pm | 1.05pm | Costume off, make-up removal & change
1.05pm | 1.20pm | Wrap — pack, meet people, load-out
1.20pm | 1.52pm | → Back to the stay | 32 min · 25 km · typical traffic for the day
1.52pm | 4.47pm | At the stay — rest
1.52pm | 2.52pm | Lunch at the stay
4.35pm | 5.21pm | → Leave the stay for Mandala Cultural Centre | 36 min · 25 km · typical traffic for the day · 10 min loading first
5.21pm | 5.51pm | Instrument & stage set-up
5.51pm | 6.21pm | Sound check
6.21pm | 7.21pm | Costume, make-up, warm-up & call
7.21pm | 7.30pm | Spare time at the venue
7.30pm | 9.00pm | INDONESIAN × INDIAN SHADOW PUPPETRY PERFORMANCE | Performance · Mandala Cultural Centre, Talaghattapura, Kanakapura Road · 25 artists
9.00pm | 9.20pm | Costume off, make-up removal & change
9.20pm | 9.50pm | Wrap — pack, meet people, load-out
9.50pm | 10.50pm | Dinner near Mandala Cultural Centre (late return)

## 13 Oct
BALI IN BENGALURU · DAILY ROUTINE
Tue, 13 Oct
Traditional Balinese Dance × Yakshagana Performance 7.00pm
• 6 Yakshagana artists (local) perform with the group today and travel on their own.
From | To | What | Where / detail
3.58pm | 5.00pm | → Leave the stay for Chowdiah Memorial Hall | 52 min · 27 km · typical traffic for the day · 10 min loading first
5.00pm | 5.30pm | Instrument & stage set-up
5.30pm | 6.00pm | Sound check
6.00pm | 7.00pm | Costume, make-up, warm-up & call
7.00pm | 9.00pm | TRADITIONAL BALINESE DANCE × YAKSHAGANA PERFORMANCE | Performance · Chowdiah Memorial Hall, Vyalikaval, Malleshwaram · 25 artists
9.00pm | 9.20pm | Costume off, make-up removal & change
9.20pm | 9.50pm | Wrap — pack, meet people, load-out
9.50pm | 10.50pm | Dinner near Chowdiah Memorial Hall (late return)

## 14 Oct
BALI IN BENGALURU · DAILY ROUTINE
Wed, 14 Oct
Mask Making Workshop 10.00am · Gamelan workshop 6.00pm
• Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
From | To | What | Where / detail
8.15am | 9.24am | → Leave the stay for PARSEC, Jayanagar (Maker's Adda) | 59 min · 35 km · typical traffic for the day · 10 min loading first
9.24am | 9.34am | Instrument & stage set-up
9.34am | 9.44am | Sound check
9.44am | 9.59am | Costume, make-up, warm-up & call
10.00am | 1.00pm | MASK MAKING WORKSHOP | Workshop · PARSEC, Jayanagar (Maker's Adda), Jayanagar 7th Block · 25 artists
1.00pm | 1.05pm | Costume off, make-up removal & change
1.05pm | 1.20pm | Wrap — pack, meet people, load-out
1.20pm | 2.18pm | → Back to the stay | 58 min · 24 km · typical traffic for the day
2.18pm | 4.08pm | At the stay — rest
2.18pm | 3.18pm | Lunch at the stay
4.08pm | 5.25pm | → Leave the stay for Jama The Studio | 1 h 07 · 36 km · typical traffic for the day · 10 min loading first
5.25pm | 5.35pm | Instrument & stage set-up
5.35pm | 5.45pm | Sound check
5.45pm | 6.00pm | Costume, make-up, warm-up & call
6.00pm | 8.00pm | GAMELAN WORKSHOP | Workshop · Jama The Studio, Jayanagar 2nd Block · 25 artists
8.00pm | 8.05pm | Costume off, make-up removal & change
8.05pm | 8.20pm | Wrap — pack, meet people, load-out
8.20pm | 9.20pm | Dinner near Jama The Studio | added: the plan has dinner back at the stay

## 15 Oct
BALI IN BENGALURU · DAILY ROUTINE
Thu, 15 Oct
Mask Making Workshop 10.00am · Balinese Shadow Puppetry Performance 7.30pm
From | To | What | Where / detail
8.15am | 9.24am | → Leave the stay for PARSEC, Jayanagar (Maker's Adda) | 59 min · 35 km · typical traffic for the day · 10 min loading first
9.24am | 9.34am | Instrument & stage set-up
9.34am | 9.44am | Sound check
9.44am | 9.59am | Costume, make-up, warm-up & call
10.00am | 1.00pm | MASK MAKING WORKSHOP | Workshop · PARSEC, Jayanagar (Maker's Adda), Jayanagar 7th Block · 25 artists
1.00pm | 1.05pm | Costume off, make-up removal & change
1.05pm | 1.20pm | Wrap — pack, meet people, load-out
1.20pm | 2.17pm | → Back to the stay | 57 min · 24 km · typical traffic for the day
2.17pm | 4.12pm | At the stay — rest
2.17pm | 3.17pm | Lunch at the stay
4.12pm | 5.30pm | → Leave the stay for Yuvapatha | 1 h 08 · 37 km · typical traffic for the day · 10 min loading first
5.30pm | 6.00pm | Instrument & stage set-up
6.00pm | 6.30pm | Sound check
6.30pm | 7.30pm | Costume, make-up, warm-up & call
7.30pm | 9.00pm | BALINESE SHADOW PUPPETRY PERFORMANCE | Performance · Yuvapatha, Jayanagar · 25 artists
9.00pm | 9.20pm | Costume off, make-up removal & change
9.20pm | 9.50pm | Wrap — pack, meet people, load-out
9.50pm | 10.50pm | Dinner near Yuvapatha
10.50pm | 11.45pm | Wait for the coach at Yuvapatha
11.45pm |  | → Leave Yuvapatha for Manipal University — overnight drive | 7 h 32 · 413 km · typical traffic for the day · sleep on the road

## 16 Oct
BALI IN BENGALURU · DAILY ROUTINE
Fri, 16 Oct
A Day in Manipal
• 6 Yakshagana artists (local) travel with the group today — 31 in the vehicles.
From | To | What | Where / detail
7.17am |  | → Arrive Manipal University after the overnight drive | 7 h 32 · 413 km · typical traffic for the day · left Yuvapatha 11.45pm on Thu, 15 Oct
7.17am | 8.47am | Freshen up & breakfast on arrival
8.47am | 9.17am | Instrument & stage set-up
9.17am | 9.47am | Sound check
9.47am | 10.00am | Costume, make-up, warm-up & call
10.00am | 4.00pm | A DAY IN MANIPAL | Performance · Manipal University, Manipal, Udupi (out of town) · 25 artists
12.00pm | 1.00pm | Lunch at the venue (packed) | During “A Day in Manipal” — arrange packed lunch.
4.00pm | 4.20pm | Costume off, make-up removal & change
4.20pm | 4.50pm | Wrap — pack, meet people, load-out
7.00pm | 8.00pm | Dinner near Manipal University
8.00pm | 11.45pm | Rest before the night drive
11.45pm |  | → Leave for the stay — overnight drive | 7 h 42 · 385 km · typical traffic for the day · home about 5.32am (+1)

## 17 Oct
BALI IN BENGALURU · DAILY ROUTINE
Sat, 17 Oct
Balinese Dance Demonstration 4.00pm
• Dinner added before leaving the venue; the plan itself has dinner at the stay after the drive back.
From | To | What | Where / detail
5.32am |  | → Arrive back at the stay from Manipal University | overnight drive · rest before the day starts
7.30am | 8.10am | Breakfast at the stay
8.10am | 12.12pm | Free at the stay — rehearsal, rest
12.00pm | 1.00pm | Lunch at the stay
12.12pm | 12.42pm | Get ready · costumes & personal kit to the vehicle
12.42pm | 1.59pm | → Leave the stay for Indian Music Experience Museum | 1 h 07 · 37 km · typical traffic for the day · 10 min loading first
1.59pm | 2.29pm | Instrument & stage set-up
2.29pm | 2.59pm | Sound check
2.59pm | 3.59pm | Costume, make-up, warm-up & call
4.00pm | 5.30pm | BALINESE DANCE DEMONSTRATION | Performance · Indian Music Experience Museum, JP Nagar 7th Phase · 25 artists
5.30pm | 5.50pm | Costume off, make-up removal & change
5.50pm | 6.20pm | Wrap — pack, meet people, load-out
6.20pm | 7.20pm | Dinner near Indian Music Experience Museum | added: the plan has dinner back at the stay

## 18 Oct
BALI IN BENGALURU · DAILY ROUTINE
Sun, 18 Oct
Closing Day 11.00am
From | To | What | Where / detail
9.08am | 10.17am | → Leave the stay for Sabha Bengaluru | 59 min · 33 km · typical traffic for the day · 10 min loading first
10.17am | 10.27am | Instrument & stage set-up
10.27am | 10.37am | Sound check
10.37am | 10.57am | Costume, make-up, warm-up & call
10.57am | 11.00am | Spare time at the venue
11.00am | 10.00pm | CLOSING DAY | Talk · Sabha Bengaluru, Shivajinagar · 25 artists
12.00pm | 1.00pm | Lunch at the venue (packed) | During “Closing Day” — arrange packed lunch.
10.00pm | 10.05pm | Costume off, make-up removal & change
10.05pm | 10.20pm | Wrap — pack, meet people, load-out
10.20pm | 11.20pm | Dinner near Sabha Bengaluru (late return)

## 19 Oct
BALI IN BENGALURU · DAILY ROUTINE
Mon, 19 Oct
Departure day
From | To | What | Where / detail
6.49pm | 7.49pm | Dinner at the stay
8.04pm | 8.14pm | Load luggage into the vehicles
8.14pm | 9.35pm | → Leave the stay for Kempegowda International Airport | 1 h 21 · 53 km · typical traffic for the day
9.35pm | 12.50am (+1) | Check-in, immigration, security | 180 min before the flight.
12.50am (+1) |  | FLIGHT DEPARTS 12.50AM (+1)